## Project Management Dashboard
Project Management Dashboard |  |  |  |  | 17-Feb-23 to 5-Oct-23
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14
Project 1 | Task 1 | Harvey | 2023-02-28 | 8 | 2023-03-09 | 3 | 37.5% | 101000 | 36756
| Task 2 | Sophia | 2023-03-02 | 9 | 2023-03-14 | 4 | 44.44% | 518000 | 230733
| Task 3 | Mike | 2023-02-20 | 5 | 2023-02-24 | 3 | 60% | 621000 | 406079
| Task 4 | Oliver | 2023-02-19 | 3 | 2023-02-22 | 3 | 100% | 822000 | 811569
| Task 5 | Louis | 2023-02-21 | 7 | 2023-03-01 | 3 | 42.86% | 377000 | 177666
| Task 6 | Harvey | 2023-02-24 | 10 | 2023-03-09 | 2 | 20% | 55000 | 12900
| Task 7 | Sophia | 2023-02-24 | 10 | 2023-03-09 | 3 | 30% | 812000 | 267179
| Task 8 | Mike | 2023-02-24 | 3 | 2023-02-28 | 0 | 0% | 696000 | 4500
Project 2 | Task 1 | Oliver | 2023-09-29 | 5 | 2023-10-05 | 2 | 40% | 223000 | 101837
| Task 10 | Mike | 2023-02-24 | 6 | 2023-03-03 | 3 | 50% | 421000 | 179515
| Task 2 | Louis | 2023-02-17 | 6 | 2023-02-24 | 3 | 50% | 398000 | 181940
| Task 3 | Harvey | 2023-02-18 | 10 | 2023-03-03 | 4 | 40% | 91000 | 35546
| Task 4 | Sophia | 2023-02-21 | 9 | 2023-03-03 | 3 | 33.33% | 737000 | 265824
| Task 5 | Mike | 2023-02-17 | 4 | 2023-02-22 | 1 | 25% | 497000 | 121350
| Task 6 | Oliver | 2023-02-20 | 6 | 2023-02-27 | 0 | 0% | 193000 | 4500
| Task 7 | Louis | 2023-02-20 | 7 | 2023-02-28 | 3 | 42.86% | 185000 | 83880
| Task 8 | Harvey | 2023-02-24 | 5 | 2023-03-02 | 2 | 40% | 587000 | 199731
| Task 9 | Sophia | 2023-02-24 | 9 | 2023-03-08 | 1 | 11.11% | 567000 | 79246
Project 3 | Task 1 | Oliver | 2023-02-18 | 7 | 2023-02-28 | 7 | 100% | 298000 | 277501
| Task 10 | Mike | 2023-02-17 | 3 | 2023-02-21 | 3 | 100% | 73000 | 69487
| Task 2 | Louis | 2023-02-17 | 9 | 2023-03-01 | 4 | 44.44% | 229000 | 62410
| Task 3 | Harvey | 2023-02-18 | 8 | 2023-03-01 | 0 | 0% | 983000 | 4500
| Task 4 | Sophia | 2023-02-20 | 7 | 2023-02-28 | 3 | 42.86% | 937000 | 383657
| Task 5 | Mike | 2023-02-21 | 4 | 2023-02-24 | 1 | 25% | 859000 | 327312
| Task 6 | Oliver | 2023-02-21 | 6 | 2023-02-28 | 3 | 50% | 86000 | 42961
| Task 7 | Louis | 2023-02-24 | 6 | 2023-03-03 | 5 | 83.33% | 174000 | 140968
| Task 8 | Harvey | 2023-02-25 | 4 | 2023-03-02 | 1 | 25% | 66000 | 16578
| Task 9 | Sophia | 2023-02-27 | 7 | 2023-03-07 | 3 | 42.86% | 650000 | 277548
Project 4 | Task 1 | Oliver | 2023-02-17 | 10 | 2023-03-02 | 5 | 50% | 844000 | 411474
| Task 2 | Louis | 2023-02-21 | 5 | 2023-02-27 | 4 | 80% | 734000 | 491639
| Task 3 | Harvey | 2023-02-24 | 7 | 2023-03-06 | 3 | 42.86% | 831000 | 302686
| Task 4 | Sophia | 2023-02-26 | 7 | 2023-03-07 | 2 | 28.57% | 900000 | 285083
| Task 5 | Mike | 2023-02-28 | 3 | 2023-03-02 | 2 | 66.67% | 346000 | 134285
Project 5 | Task 1 | Oliver | 2023-03-02 | 9 | 2023-03-14 | 8 | 88.89% | 792000 | 731688
| Task 2 | Louis | 2023-03-02 | 10 | 2023-03-15 | 2 | 20% | 233000 | 52380
| Task 3 | Harvey | 2023-02-17 | 4 | 2023-02-22 | 0 | 0% | 152000 | 4500
| Task 4 | Sophia | 2023-02-19 | 8 | 2023-03-01 | 5 | 62.5% | 343000 | 209623
| Task 5 | Mike | 2023-02-24 | 10 | 2023-03-09 | 3 | 30% | 862000 | 310449
| Task 6 | Oliver | 2023-02-25 | 6 | 2023-03-06 | 3 | 50% | 607000 | 326871
| Task 7 | Louis | 2023-02-25 | 4 | 2023-03-02 | 2 | 50% | 995000 | 455940
Grand Total | [7 empty] | 19895000 | 8520291
Working Terminology
Not Started | 4 |  | Sum of Days completed |  | 112 |  | Attribute | Actual | Budget
In Progress | 33 |  | Sum of Duration |  | 266 |  | Sum | 8520291 | 19895000
Completed | 3 | [5 empty] | Percentage | 42.83% | 57.17%
Remaining | 37 |  | Days Completed |  | 42.11%
Total Tasks | 40 |  | Days Remaining |  | 57.89% |  | Scroll Bar | 0
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Terminology (hidden)
Values |  |  | Actual | Budget
Sum of Days completed | 112 | BarChart | 17040582 | 39790000
Sum of Duration | 266 | Doughnut Chart | 42.83% | 57.17%

## Project Management Data
Project Management Data
| Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
| Project 2 | Task 1 | Oliver | 2023-09-29 | 5 | 2023-10-05 | 2 | 40% | 223000 | 101837
| Project 2 | Task 2 | Louis | 2023-02-17 | 6 | 2023-02-24 | 3 | 50% | 398000 | 181940
| Project 2 | Task 3 | Harvey | 2023-02-18 | 10 | 2023-03-03 | 4 | 40% | 91000 | 35546
| Project 2 | Task 4 | Sophia | 2023-02-21 | 9 | 2023-03-03 | 3 | 33.33% | 737000 | 265824
| Project 2 | Task 5 | Mike | 2023-02-17 | 4 | 2023-02-22 | 1 | 25% | 497000 | 121350
| Project 2 | Task 6 | Oliver | 2023-02-20 | 6 | 2023-02-27 | 0 | 0% | 193000 | 4500
| Project 2 | Task 7 | Louis | 2023-02-20 | 7 | 2023-02-28 | 3 | 42.86% | 185000 | 83880
| Project 2 | Task 8 | Harvey | 2023-02-24 | 5 | 2023-03-02 | 2 | 40% | 587000 | 199731
| Project 2 | Task 9 | Sophia | 2023-02-24 | 9 | 2023-03-08 | 1 | 11.11% | 567000 | 79246
| Project 2 | Task 10 | Mike | 2023-02-24 | 6 | 2023-03-03 | 3 | 50% | 421000 | 179515
| Project 3 | Task 1 | Oliver | 2023-02-18 | 7 | 2023-02-28 | 7 | 100% | 298000 | 277501
| Project 3 | Task 2 | Louis | 2023-02-17 | 9 | 2023-03-01 | 4 | 44.44% | 229000 | 62410
| Project 3 | Task 3 | Harvey | 2023-02-18 | 8 | 2023-03-01 | 0 | 0% | 983000 | 4500
| Project 3 | Task 4 | Sophia | 2023-02-20 | 7 | 2023-02-28 | 3 | 42.86% | 937000 | 383657
| Project 3 | Task 5 | Mike | 2023-02-21 | 4 | 2023-02-24 | 1 | 25% | 859000 | 327312
| Project 3 | Task 6 | Oliver | 2023-02-21 | 6 | 2023-02-28 | 3 | 50% | 86000 | 42961
| Project 3 | Task 7 | Louis | 2023-02-24 | 6 | 2023-03-03 | 5 | 83.33% | 174000 | 140968
| Project 3 | Task 8 | Harvey | 2023-02-25 | 4 | 2023-03-02 | 1 | 25% | 66000 | 16578
| Project 3 | Task 9 | Sophia | 2023-02-27 | 7 | 2023-03-07 | 3 | 42.86% | 650000 | 277548
| Project 3 | Task 10 | Mike | 2023-02-17 | 3 | 2023-02-21 | 3 | 100% | 73000 | 69487
| Project 4 | Task 1 | Oliver | 2023-02-17 | 10 | 2023-03-02 | 5 | 50% | 844000 | 411474
| Project 4 | Task 2 | Louis | 2023-02-21 | 5 | 2023-02-27 | 4 | 80% | 734000 | 491639
| Project 4 | Task 3 | Harvey | 2023-02-24 | 7 | 2023-03-06 | 3 | 42.86% | 831000 | 302686
| Project 4 | Task 4 | Sophia | 2023-02-26 | 7 | 2023-03-07 | 2 | 28.57% | 900000 | 285083
| Project 4 | Task 5 | Mike | 2023-02-28 | 3 | 2023-03-02 | 2 | 66.67% | 346000 | 134285
| Project 5 | Task 1 | Oliver | 2023-03-02 | 9 | 2023-03-14 | 8 | 88.89% | 792000 | 731688
| Project 5 | Task 2 | Louis | 2023-03-02 | 10 | 2023-03-15 | 2 | 20% | 233000 | 52380
| Project 5 | Task 3 | Harvey | 2023-02-17 | 4 | 2023-02-22 | 0 | 0% | 152000 | 4500
| Project 5 | Task 4 | Sophia | 2023-02-19 | 8 | 2023-03-01 | 5 | 62.5% | 343000 | 209623
| Project 5 | Task 5 | Mike | 2023-02-24 | 10 | 2023-03-09 | 3 | 30% | 862000 | 310449
| Project 5 | Task 6 | Oliver | 2023-02-25 | 6 | 2023-03-06 | 3 | 50% | 607000 | 326871
| Project 5 | Task 7 | Louis | 2023-02-25 | 4 | 2023-03-02 | 2 | 50% | 995000 | 455940
| Project 1 | Task 1 | Harvey | 2023-02-28 | 8 | 2023-03-09 | 3 | 37.5% | 101000 | 36756
| Project 1 | Task 2 | Sophia | 2023-03-02 | 9 | 2023-03-14 | 4 | 44.44% | 518000 | 230733
| Project 1 | Task 3 | Mike | 2023-02-20 | 5 | 2023-02-24 | 3 | 60% | 621000 | 406079
| Project 1 | Task 4 | Oliver | 2023-02-19 | 3 | 2023-02-22 | 3 | 100% | 822000 | 811569
| Project 1 | Task 5 | Louis | 2023-02-21 | 7 | 2023-03-01 | 3 | 42.86% | 377000 | 177666
| Project 1 | Task 6 | Harvey | 2023-02-24 | 10 | 2023-03-09 | 2 | 20% | 55000 | 12900
| Project 1 | Task 7 | Sophia | 2023-02-24 | 10 | 2023-03-09 | 3 | 30% | 812000 | 267179
| Project 1 | Task 8 | Mike | 2023-02-24 | 3 | 2023-02-28 | 0 | 0% | 696000 | 4500
Formulas:
End Date = WORKDAY.INTL([Start Date]-1,[Duration],1)